## Sheet1
PRODUCT BACKLOG
| ID | USER STORY | OWNER | PRIORITY | EFFORT IN STORY POINTS | STATUS | DEFINITION OF DONE | NOTES
| U1.1 | As an unregistered user, I want to open the home page. So that I can log in or sign up. | PRODUCT OWNER | HIGH | 7 | To Do | Landing page is accessible on our website. Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| U1.2 | As an unregistered user, I want to visit sign up page,. So that I can fill my details. | PRODUCT OWNER | HIGH | 7 | To Do | The sign-up page is accessible on our website. Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| A1.1 | As an admin/worker, I want to log in. So that I can see my dashboard. | PRODUCT OWNER | HIGH | 7 | To Do | The login page is accesible. Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| U1.3 | As a customer, I want to log in. So that I can see the booking page. | PRODUCT OWNER | HIGH | 5 | To Do | The login page is accesible. Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| U1.4 | As a customer, I want to create an account. So that I can have an account for booking an appointment for service. | PRODUCT OWNER | HIGH | 8 | To Do | User can book services on our website. Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| U1.5 | As a customer , I want to view my account details . So that I can make sure they're correct | PRODUCT OWNER | HIGH | 5 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| U1.6 | As a customer , I want to be able edit my details . So that I can change my details | PRODUCT OWNER | HIGH | 5 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| U1.7 | As a customer , I want to cancel appointments I made, So that I can change my mind before the appointment. | PRODUCT OWNER | HIGH | 7 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| A1.2 | As an Admin , I want to be able to create an employee user So that I can add workers to the system | PRODUCT OWNER | HIGH | 6 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| A1.3 | As an Admin , I want to be able to delete an employee user account . So that I can remove former workers from the system. | PRODUCT OWNER | HIGH | 5 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| A1.4 | As a Admin , I want to edit employees details . So that I can ensure I have the correct and most up to date information about them. | PRODUCT OWNER | HIGH | 5 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| A1.5 | As a admin , I want to edit employee shift schedules . So that I can easily allocate work to my employees. | PRODUCT OWNER | HIGH | 7 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| A1.6 | As an admin, I want to view a summary of all past and present bookings, sorted by date . So that I can make organising my schedule must easier. | PRODUCT OWNER | HIGH | 7 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| A1.7 | As an admin , I want to be able to view all my employees availability . So that organising their work schedule can be easy and fair. | PRODUCT OWNER | HIGH | 5 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| A1.8 | As a customer , I want to view all available bookings and the employee available. So that I can pick the best time for my personal schedule. | PRODUCT OWNER | HIGH | 7 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| U1.8 | As a customer , I want to create a booking at my preferred date, time and employee. So that I can pick the best time for my personal schedule. | PRODUCT OWNER | HIGH | 7 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| E1.1 | As a Worker (Employee) , I want to be able to view my current profile . So that I can view my details. | PRODUCT OWNER | HIGH | 5 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| E1.2 | As a Worker (Employee) , I want to be able to edit my current profile . So that I can view my keep my personal information up to date | PRODUCT OWNER | HIGH | 5 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| E1.3 | As a Worker (Employee) , I want to be able to view my assigned working hours/days . So that I know when I will be required to work next. | PRODUCT OWNER | HIGH | 7 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| E1.4 | As a Worker (Employee) , I want to be able to view what services I need to provide during my shift . So that I can prepare for my upcoming shift accordingly. | PRODUCT OWNER | HIGH | 7 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.
| U1.9 | As a customer, I want to be able to view the history of my bookings . So that I can check the status of my old and new bookings. | PRODUCT OWNER | HIGH | 5 | To Do | Code reviewed and commented. Unit tests successful. Acceptance tests successful.