## Sheet1
SPRINT-1 BACKLOG
| PBI ID | PBI Name | Task ID | Task | Assigned To | Not Started | In Progress | Completed | Notes
| U1.1 | "As an unregistered user, I want to open the home page. So that I can log in or sign up." | U1.1.1 | Create a mockup design of landing page for users | Arone |  |  | x
|  |  | U1.1.2 | Implement the front end of landing page on mockup design | Arone & Tein |  |  | x
|  |  | U1.1.4 | Testing the front end home page | Tein |  |  | x
| U1.10 | As a customer, I want to be able to view the history of my bookings. So that I can check the status of my old and new bookings. | U1.10.1 | Create a mockup design of Customer booking System | Arone |  | x
|  |  | U1.10.2 | Implement the front end of booking history | Arone , Todd and Dylan |  | x
|  |  | U1.10.3 | Implement the back end of booking history | Man |  | x
|  |  | U1.10.4 | Testing the booking history frontend | Arone |  | x
|  |  | U1.10.5 | Testing the booking history backend | Man |  | x
| U1.9 | As a customer , I want to create a booking at my preferred date, time and employee. So that I can pick the best time for my personal schedule. | U1.9.1 | Create a mockup design of Customer booking System | Arone |  | x
|  |  | U1.9.2 | Implement the front end of creating booking | Arone , Todd and Dylan |  | x
|  |  | U1.9.3 | Implement the back end of creating booking | Man |  | x
|  |  | U1.9.4 | Testing the create booking frontend | Arone , Todd and Dylan |  | x
|  |  | U1.9.5 | Testing the create booking backend | Man |  | x
| U1.8 | As a customer , I want to view all available bookings and the employee available. So that I can pick the best time for my personal schedule. | U1.8.1 | Create a mockup design of Customer booking System | Arone |  | x
|  |  | U1.8.2 | Implement the front end of available bookings | Arone , Todd and Dylan |  | x
|  |  | U1.8.3 | Implement the back end of available bookings | Man |  | x
|  |  | U1.8.4 | Testing the available bookings frontend | Arone , Todd and Dylan |  | x
|  |  | U1.8.5 | Testing the available bookings backend | Man |  | x