## Sheet1
SPRINT-3 BACKLOG
| PBI ID | PBI Name | Task ID | Task | Assigned To | Not Started | In Progress | Completed | Notes
| A1.7 | As an admin, I want to be able to view all my employees availability. So that organising their work schedule can be easy and fair. | A1.7.1 | Create a mockup design for Admin Dashboard | Arone |  |  | x
|  |  | A1.7.2 | Implement the front end of viewing employee availability on mockup design | Arone & Dylan |  |  | x
|  |  | A1.7.3 | Implement the back end of viewing employee availability | Man |  |  | x
|  |  | A1.7.4 | Testing the viewing employee availability frontend | Arone & Dylan |  |  | x
|  |  | A1.7.5 | Testing theviewing employee availability backend | Man |  |  | x
| U1.2 | As an unregistered user, I want to visit sign up page,. So that I can fill my details. | U1.2.1 | Create a mockup design of User Sign up page | Arone |  |  | x
|  |  | U1.2.2 | Implement the front end of user sign up on mockup design | Arone & Todd |  |  | x
|  |  | U1.2.3 | Implement the back end of user sign upuser | Man |  |  | x
|  |  | U1.2.4 | Testing the delete user sign up | Arone & Todd |  |  | x
|  |  | U1.2.5 | Testing the delete user sign up | Man |  |  | x
| E1.4 | As a Worker (Employee) , I want to be able to view what services I need to provide during my shift . So that I can prepare for my upcoming shift accordingly. | E1.4.1 | Create a mockup design of Employee Dashboard | Arone |  |  | x
|  |  | E1.4.2 | Implement the front end of employee viewing his responsibility on mockup design | Arone & Tein |  |  | x
|  |  | E1.4.3 | Implement the back end of employee viewing his responsibility | Man |  |  | x
|  |  | E1.4.4 | Testing the employee viewing his responsibility | Arone & Tein | x
|  |  | E1.4.5 | Testing the employee viewing his responsibility | Man | x
| U1.7 | As a customer , I want to cancel appointments I made, So that I can change my mind before the appointment. | U1.7.1 | Create a mockup design of Customer cancelling appointment | Arone |  |  | x
|  |  | U1.7.2 | Implement the front end of customer cancelling appointment | Arone , Todd and Dylan |  |  | x
|  |  | U1.7.3 | Implement the back end of customer cancelling appointment | Man |  |  | x
|  |  | U1.7.4 | Testing the customer cancelling appointment | Arone | x
|  |  | U1.7.5 | Testing thecustomer cancelling appointment | Man | x
| E1.2 | As a Worker (Employee) , I want to be able to edit my current profile . So that I can view my keep my personal information up to date | E1.2.1 | Create a mockup design of Employee Dashboard | Arone |  |  | x
|  |  | E1.2.2 | Implement the front end of employee updating the personal details | Arone , Todd and Dylan |  |  | x
|  |  | E1.2.3 | Implement the back end of employee updating the personal details | Man |  |  | x
|  |  | E1.2.4 | Testing the employee updating the personal details | Arone | x
|  |  | E1.2.5 | Testing the employee updating the personal details | Man | x