## Sheet1
SPRINT-2 BACKLOG
| PBI ID | PBI Name | Task ID | Task | Assigned To | Not Started | In Progress | Completed | Notes
| A1.2 | As an Admin , I want to be able to create an employee user So that I can add workers to the system | A1.1.1 | Create a mockup design of Admin System | Arone |  |  | x
|  |  | A1.1.2 | Implement the front end of create an employee user on mockup design | Arone & Dylan |  |  | x
|  |  | A1.1.3 | Implement the back end of creating an eomployee user | Man |  |  | x
|  |  | A1.1.4 | Testing the create an employee user frontend | Arone & Dylan | x
|  |  | A1.1.5 | Testing the create an employee user backend | Man | x |  | x
| A1.3 | "As an Admin, I want to be able to delete an employee user account. So that I can remove former workers from the system." | A1.10.1 | Create a mockup design of Admin System | Arone |  |  | x
|  |  | A1.10.2 | Implement the front end of delete an employee user on mockup design | Arone & Todd |  |  | x
|  |  | A1.10.3 | Implement the back end of deleting an eomployee user | Man |  |  | x
|  |  | A1.10.4 | Testing the delete an employee user frontend | Arone & Todd | x
|  |  | A1.10.5 | Testing the delete an employee user backend | Man | x
| A1.4 | "As a Admin, I want to edit employees details. So that I can ensure I have the correct and most up to date information about them." | A1.9.1 | Create a mockup design of Admin System | Arone |  |  | x
|  |  | A1.9.2 | Implement the front end of editing an employee user on mockup design | Arone & Tein |  |  | x
|  |  | A1.9.3 | Implement the back end of editing an eomployee user | Man |  |  | x
|  |  | A1.9.4 | Testing the editing an employee user frontend | Arone & Tein | x
|  |  | A1.9.5 | Testing the editing an employee user backend | Man | x
| A1.6 | "As an admin, I want to view a summary of all past and present bookings, sorted by date. So that I can make organising my schedule must easier." | A1.8.1 | Create a mockup design of Admin System | Arone |  |  | x
|  |  | A1.8.2 | Implement the front end of viewing booking summary on mockup design | Arone & Tein |  |  | x
|  |  | A1.8.3 | Implement the back end of viewing booking summary | Man |  |  | x
|  |  | A1.8.4 | Testing the viewing booking summary frontend | Arone & Tein | x
|  |  | A1.8.5 | Testing the viewing booking summary backend | Man | x
| U1.6 | As a customer , I want to be able edit my details . So that I can change my details | U1.6.1 | Create a mockup design of Customer Profile System | Arone |  |  | x
|  |  | U1.6.2 | Implement the front end of customer editing details | Arone , Todd and Dylan |  |  | x
|  |  | U1.6.3 | Implement the back end of customer editing details | Man |  |  | x
|  |  | U1.6.4 | Testing the customer editing details frontend | Arone | x
|  |  | U1.6.5 | Testing the customer editing details backend | Man | x
| U1.5 | As a customer , I want to view my account details . So that I can make sure they're correct | U1.5.1 | Create a mockup design of Customer Profile System | Arone |  |  | x
|  |  | U1.5.2 | Implement the front end of customer viewing account details | Arone , Todd and Dylan |  |  | x
|  |  | U1.5.3 | Implement the back end of customer viewing account details | Man |  |  | x
|  |  | U1.5.4 | Testing the customer viewing account details frontend | Arone | x
|  |  | U1.5.5 | Testing the customer viewing account details backend | Man | x
| U1.10 | As a customer, I want to be able to view the history of my bookings. So that I can check the status of my old and new bookings. | U1.10.1 | Create a mockup design of Customer booking System | Arone |  |  | x
|  |  | U1.10.2 | Implement the front end of booking history | Arone , Todd and Dylan |  |  | x
|  |  | U1.10.3 | Implement the back end of booking history | Man |  |  | x
|  |  | U1.10.4 | Testing the booking history frontend | Arone | x
|  |  | U1.10.5 | Testing the booking history backend | Man | x
| U1.9 | As a customer , I want to create a booking at my preferred date, time and employee. So that I can pick the best time for my personal schedule. | U1.9.1 | Create a mockup design of Customer booking System | Arone |  |  | x
|  |  | U1.9.2 | Implement the front end of creating booking | Arone , Todd and Dylan |  |  | x
|  |  | U1.9.3 | Implement the back end of creating booking | Man |  |  | x
|  |  | U1.9.4 | Testing the create booking frontend | Arone , Todd and Dylan |  |  | x
|  |  | U1.9.5 | Testing the create booking backend | Man |  |  | x
| U1.8 | As a customer , I want to view all available bookings and the employee available. So that I can pick the best time for my personal schedule. | U1.8.1 | Create a mockup design of Customer booking System | Arone |  |  | x
|  |  | U1.8.2 | Implement the front end of available bookings | Arone , Todd and Dylan |  |  | x
|  |  | U1.8.3 | Implement the back end of available bookings | Man |  |  | x
|  |  | U1.8.4 | Testing the available bookings frontend | Arone , Todd and Dylan |  |  | x
|  |  | U1.8.5 | Testing the available bookings backend | Man |  |  | x